## Slide 1: Credentialing System
Stefana Rusu, Devon Fairman, Tyler Palmer

## Slide 2: Introduction
Project Information
  Credentialing and Scheduling
Scope
  Create more efficiency
Deliverables
  Database
  MVC App
  Technical Document
  Testing Plan
  Deployment Plan
Team qualifications
  Computer Science Majors
  Wide variety of experience
Notes: Notes:
Experience:
    C#
    SQL
    MVC
    Project Management
    Research & Analysis

## Slide 3: Final Status Report
Review of Project
  Beginning
  End
High-Level Status
  Sprint 7
  Overall
Detailed Status
  Sprint 7
  Overall
Risks
  Critical
  Mitigation
Reflection
  Challenges
  Triumphs
Issues
  Open issues
  Error Log
Technical Documentation
  High Level
  Error Handling
Conclusion
Notes: Make additional slides for the above information.

## Slide 4: Project Recap
Beginning
Strong start
ERD focus
Regular team meetings
Regular stakeholder meetings
End
Moderate finish
MVC Focus
48.65% of use cases functional
16.22% of use cases partially complete (database only)
Implementation incomplete
Thorough documentation

## Slide 5: High Level Status
Sprint 7
  Updated Database
  Updated MVC
  Updated Technical Document
  Updated Test Plan
  Updated Analytical Report
Overall
  Completed 77.78% (56/72) of the tasks for the project
  Completed 69.69% (410.5/589) of the hours for the project
  Negative trends have fluctuated
Notes: Negative trends have varied. A negative trend that has followed us to the end of the project is the fact that we were not able to complete all the use cases. There are still various tables and stored procedures that have not been implemented in MVC.

## Slide 6: Detailed Status
Sprint 7
  Updated stored procedures (Qualifications, Instructors)
  Updated MVC
    Layout and color scheme
    Implemented error handling for all current models
    “SharedError” view
  Finalized Analytical Report, Test Plan, Technical Document
Overall
              Created a solid data model (ERD)
              Created a solid plan and documentation
              MVC app is functional but incomplete
              Certain errors have been found but time did not allow for fixing them
              Project ready for next team
Notes:   Updated MVC - a “sharedError” view was created to display an error page - instead of each controller having its own Error view, all the controllers redirect to it if an error occurs
  Finalized Analytical Report, Test Plan, Technical Document
    Analytical report contains high-level information about the project (SWOT analysis, use case diagrams) - everything needed to get familiar with the project.
    Technical Design document contains detailed status about the project, the definitions for certain ERD choices and tables, and the processing logic for the MVC app and error handling
    Test Plan contains testing for certain features such as Add Course, Update Campus, and Search Room.
  Created a solid data model (ERD) that future teams can utilize and continue building upon the project
  Certain errors have been found but time did not allow for fixing them - they have been logged with details

## Slide 7: Sprint 7 Tasks

## Slide 8: Risks
Critical Risks
  Estimation and Scheduling
  Growth in Requirements
  Conflicting Requirements from Stakeholders
  Scope Creep
Mitigation
  Research
  Stakeholder prioritization/compromise
Consequences
  Project completion (incompletion)
  Milestone delays
  Team member stress
Notes: Devon

## Slide 9: Reflection
Challenges
  Requirements
  Technologies
Triumphs
  Technologies
  Documentation
Notes: Tyler
Requirements - First time doing that kind of requirements gathering.
Technologies - Git, Bootstrap, MVC

## Slide 10: Reflection Cont.
What worked?
  Source Code Control
  Research and Feedback
  Organization
What didn’t work?
  File Organization
  Communication
What would you do differently?
  Collaboration
  Organization - Trello
  UML, Design Plan & Testing
  PM Schedule Consistency
Notes: Tyler
Organization - Google Drive became a mess at one point.
Source Code Control - Git did it’s job.

## Slide 11: Issues
Open Issues
  ERD Issues
  Changing Requirements
Error Log
  Issues in the MVC
  Database logical error
  Package Error
    Issues with technology
Notes: Devon

## Slide 12: Technical Documentation
Error Handling
Global error handling
ModelInquire generic
Data access layer returns a model of that type (Room, Campus, etc)
  Contains status code
  Contains status description
Transition Plan
Thorough Technical Documentation
Access to all other documentation
  SWOT analysis
  ERD
  Final Report
  Testing Data
Testing Plan
Were able to check off use cases off the list
Future template for other teams taking over
  Contains info about testing strategy
  Contains test cases
Testing data
Notes: The ModelInquire class is built to facilitate error handling. Data access layers will return this, containing the model of a specific type (single object, list, etc.) along with a status code and status description.
For models that return a list, a negative status code will return specific error messages while positive status code will signify the number of records found.
For models that return a single object, negative numbers will return a specific error message, 0 will signify that no record was found, and greater than 1 will signify that multiple records were found for the search criteria.

## Slide 13: Conclusion
Notes: Tyler

## Slide 14: Demo
Course Add
Building Update
Room Search