## Project Plan
Sprint | Task | Resource | Start Date | Due Date | Planned Hours | Actual Hours | Status
Sprint 1: Business Alignment and User Research | Team Formation
9/5/18 - 9/19/18 |  | Stefana | 2018-09-05 | 2018-09-05 | 1 | 1 | Complete
|  | Devon | 2018-09-05 | 2018-09-05 | 1 | 1 | Complete
|  | Tyler | 2018-09-05 | 2018-09-05 | 1 | 1 | Complete
Project Scope
|  | Stefana | 2018-09-05 | 2018-09-19 | 2 | 2 | Complete
|  | Devon | 2018-09-05 | 2018-09-19 | 2 | 2 | Complete
|  | Tyler | 2018-09-05 | 2018-09-19 | 2 | 2 | Complete
Roles Assigned
|  | Stefana | 2018-09-05 | 2018-09-10 | 0.5 | 0.5 | Complete
|  | Devon | 2018-09-05 | 2018-09-10 | 0.5 | 0.5 | Complete
|  | Tyler | 2018-09-05 | 2018-09-10 | 0.5 | 0.5 | Complete
| Course Time | All | 2018-09-05 | 2018-09-19 | 6 | 6 | Complete
Project Assessment
|  | Stefana | 2018-09-05 | 2018-09-19 | 2 | 1.5 | Complete
|  | Devon | 2018-09-05 | 2018-09-19 | 2 | 2 | Complete
|  | Tyler | 2018-09-05 | 2018-09-19 | 2 | 2 | Complete
Project Concept Draft
|  | Stefana | 2018-09-05 | 2018-09-12 | 2 | 1 | Complete
|  | Devon | 2018-09-05 | 2018-09-12 | 2 | 1 | Complete
|  | Tyler | 2018-09-05 | 2018-09-12 | 2 | 1 | Complete
| Project Schedule | Stefana | 2018-09-12 | 2018-09-19 | 2 | 2 | Complete
| Project Plan | Stefana | 2018-09-12 | 2018-09-19 | 4 | 5 | Complete
| Project Requirements | Tyler | 2018-09-12 | 2018-09-19 | 2 | 1 | Incomplete
| Stakeholder Meeting | Stefana | 2018-09-19 | 2018-09-19 | 2 | 2 | Complete
| Status Report | Stefana | 2018-09-12 | 2018-09-19 | 1.5 | 2 | Complete
| Draft Preliminary Software Plan | Devon | 2018-09-12 | 2018-09-19 | 2 | 2 | Complete
Research
|  | Stefana | 2018-09-05 | 2018-09-19 | 10 | 5 | Incomplete
|  | Devon | 2018-09-05 | 2018-09-19 | 10 | 4 | Incomplete
|  | Tyler | 2018-09-05 | 2018-09-19 | 10 | 3 | Incomplete
| Sprint 1 Milestone |  |  |  | 0 | 0
Overall |  |  |  |  | 72 | 51
Sprint 2: Project Kick-Off and Design | Identify processes and requirements
9/19/18 - 10/3/18 |  | Stefana | 2018-09-19 | 2018-10-03 | 5 | 3 | Incomplete
|  | Devon | 2018-09-19 | 2018-10-03 | 5 | 3 | Incomplete
|  | Tyler | 2018-09-19 | 2018-10-03 | 5 | 3 | Incomplete
| Develop Functional Specifications | Devon | 2018-09-19 | 2018-10-03 | 3 | 3 | Complete
Project Concept
|  | Stefana | 2018-09-19 | 2018-09-26 | 1 | 1 | Complete
|  | Devon | 2018-09-19 | 2018-09-26 | 1 | 1 | Complete
|  | Tyler | 2018-09-19 | 2018-09-26 | 1 | 1 | Complete
| Course Time | All | 2018-09-19 | 2018-10-03 | 6 | 6 | Complete
| SWOT Analysis | Stefana | 2018-09-19 | 2018-10-03 | 3 | 3 | Complete
| Risk Assessment | Tyler | 2018-09-19 | 2018-09-26 | 3 | 3 | Complete
| Update Project Concept and Plan | Stefana | 2018-09-26 | 2018-10-03 | 1 | 1 | Complete
Establish Naming Conventions
|  | Stefana | 2018-09-19 | 2018-09-26 | 0.5 | 0.5 | Complete
|  | Devon | 2018-09-19 | 2018-09-26 | 0.5 | 0.5 | Complete
|  | Tyler | 2018-09-19 | 2018-09-26 | 0.5 | 0.5 | Complete
Analyze Textbook System
|  | Stefana | 2018-09-19 | 2018-10-03 | 5 | 3 | Incomplete
|  | Devon | 2018-09-19 | 2018-10-03 | 5 | 2 | Incomplete
|  | Tyler | 2018-09-19 | 2018-10-03 | 5 | 5 | Complete
Design Database (UML)
|  | Stefana | 2018-09-19 | 2018-10-03 | 5 | 3 | Incomplete
|  | Devon | 2018-09-19 | 2018-10-03 | 5 | 3 | Incomplete
|  | Tyler | 2018-09-19 | 2018-10-03 | 5 | 3 | Incomplete
Research & Process Refinement
|  | Stefana | 2018-09-19 | 2018-10-03 | 10 | 6 | Incomplete
|  | Devon | 2018-09-19 | 2018-10-03 | 10 | 4 | Incomplete
|  | Tyler | 2018-09-19 | 2018-10-03 | 10 | 4 | Incomplete
| Sprint 2 Milestone |  |  |  | 0 | 0
Overall |  |  |  |  | 95.5 | 62.5
Sprint 3: Prototype | Review Specifications and Construct Use Cases
10/3/18 - 10/17/18 |  | Stefana | 2018-10-03 | 2018-10-05 | 2 | 2 | Complete
|  | Devon | 2018-10-03 | 2018-10-05 | 2 | 2 | Complete
|  | Tyler | 2018-10-03 | 2018-10-05 | 2 | 2 | Complete
Refine ERD
|  | Stefana | 2018-10-03 | 2018-10-05 | 2 | 2 | Complete
|  | Devon | 2018-10-03 | 2018-10-05 | 2 | 2 | Complete
|  | Tyler | 2018-10-03 | 2018-10-05 | 2 | 2 | Complete
| Update Project Concept | Stefana | 2018-10-03 | 2018-10-10 | 0.5 | 0.5 | Complete
| Update Design Document | Stefana | 2018-10-03 | 2018-10-10 | 0.5 | 0.5 | Complete
| Course Time | All | 2018-10-03 | 2018-10-17 | 6 | 6 | Complete
Assign Development Resources
|  | Stefana | 2018-10-10 | 2018-10-17 | 1 | 1 | Complete
|  | Devon | 2018-10-10 | 2018-10-17 | 1 | 1 | Complete
|  | Tyler | 2018-10-10 | 2018-10-17 | 1 | 1 | Complete
Start Initial Build of Database
|  | Stefana | 2018-10-10 | 2018-10-17 | 2 | 1 | Postponed
|  | Devon | 2018-10-10 | 2018-10-17 | 2 | 0 | Postponed
|  | Tyler | 2018-10-10 | 2018-10-17 | 2 | 0 | Postponed
MVC Technical Design Document and Class UML
|  | Stefana | 2018-10-10 | 2018-10-17 | 8 | 5 | Postponed
|  | Devon | 2018-10-10 | 2018-10-17 | 8 | 3 | Postponed
|  | Tyler | 2018-10-10 | 2018-10-17 | 8 | 0 | Postponed
Develop Database Code (SQL)
|  | Stefana | 2018-10-10 | 2018-10-17 | 10 | 2 | Postponed
|  | Devon | 2018-10-10 | 2018-10-17 | 10 | 0 | Postponed
|  | Tyler | 2018-10-10 | 2018-10-17 | 10 | 0 | Postponed
Refine ERD and Deliver as Prototype
|  | Stefana | 2018-10-17 | 2018-10-17 | 3 | 5 | Complete
|  | Devon | 2018-10-17 | 2018-10-17 | 3 | 1 | Incomplete
|  | Tyler | 2018-10-17 | 2018-10-17 | 3 | 1 | Incomplete
Research
|  | Stefana | 2018-10-03 | 2018-10-17 | 1.5 | 6 | Complete
|  | Devon | 2018-10-03 | 2018-10-17 | 1.5 | 3 | Complete
|  | Tyler | 2018-10-03 | 2018-10-17 | 1.5 | 1.5 | Complete
| Sprint 3 Milestone |  |  |  | 0 | 0
Overall |  |  |  |  | 95.5 | 50.5
Sprint 4: System Design | Review Use Cases
10/17/18 - 10/31/18 |  | Stefana | 2018-10-17 | 2018-10-20 | 1 | 1 | Complete
|  | Devon | 2018-10-17 | 2018-10-20 | 2 | 2 | Complete
|  | Tyler | 2018-10-17 | 2018-10-20 | 1 | 1 | Complete
| Construct Use Case Diagram | Stefana | 2018-10-20 | 2018-10-20 | 2 | 2 | Complete
Refine ERD and UML
|  | Stefana | 2018-10-17 | 2018-10-20 | 2 | 2 | Complete
|  | Tyler | 2018-10-17 | 2018-10-20 | 2 | 2 | Complete
| Course Time | All | 2018-10-17 | 2018-10-31 | 6 | 6 | Complete
Update Technical Document, Status Report and Project Plan
|  | Stefana | 2018-10-17 | 2018-10-31 | 2 | 4 | Complete
|  | Devon | 2018-10-17 | 2018-10-24 | 2 | 2 | Complete
|  | Tyler | 2018-10-17 | 2018-10-24 | 2 | 2 | Complete
Assign Development Resources
|  | Stefana | 2018-10-17 | 2018-10-20 | 0.5 | 0.5 | Complete
|  | Devon | 2018-10-17 | 2018-10-20 | 0.5 | 0.5 | Complete
|  | Tyler | 2018-10-17 | 2018-10-20 | 0.5 | 0.5 | Complete
Start Initial Build of Database (See WBS)
|  | Stefana | 2018-10-20 | 2018-10-24 | 5 | 5 | Complete
|  | Devon | 2018-10-20 | 2018-10-24 | 5 | 5 | Complete
|  | Tyler | 2018-10-20 | 2018-10-24 | 5 | 5 | Complete
MVC Technical Design Document and Class UML
|  | Stefana | 2018-10-24 | 2018-10-31 | 3 | 1 | Remaining/Postponed
|  | Devon | 2018-10-24 | 2018-10-31 | 5 | 1 | Remaining/Postponed
|  | Tyler | 2018-10-24 | 2018-10-31 | 7 | 0 | Remaining/Postponed
Develop Database Code
|  | Stefana | 2018-10-24 | 2018-10-31 | 6 | 6 | Complete
|  | Devon | 2018-10-24 | 2018-10-31 | 6 | 4 | Incomplete
|  | Tyler | 2018-10-24 | 2018-10-31 | 6 | 6 | Complete
Research
|  | Stefana | 2018-10-17 | 2018-10-31 | 5 | 5 | Complete
|  | Devon | 2018-10-17 | 2018-10-31 | 4 | 4 | Complete
|  | Tyler | 2018-10-17 | 2018-10-31 | 1 | 1 | Complete
| Sprint 4 Milestone |  |  |  | 0 | 0
Overall |  |  |  |  | 81.5 | 68.5
Sprint 5: Alpha Testing & Project Report | Project Report Outline
10/31/18 - 11/14/18 |  | Stefana | 2018-10-31 | 2018-11-07 | 1 | 1 | Complete
Project Report Draft
|  | Stefana | 2018-10-31 | 2018-11-07 | 2 | 2 | Complete
|  | Devon | 2018-10-31 | 2018-11-07 | 1.5 | 1.5 | Complete
|  | Tyler | 2018-10-31 | 2018-11-07 | 1 | 0 | Incomplete
Project Report Presentation Draft
|  | Stefana | 2018-11-07 | 2018-11-10 | 0.5 | 0.5 | Complete
Update Technical Document
|  | Stefana | 2018-10-31 | 2018-11-14 | 1 | 1 | Complete
Update Status Report & Project Plan
|  | Stefana | 2018-10-31 | 2018-11-07 | 1 | 1 | Complete
|  | Tyler | 2018-11-07 | 2018-11-14 | 1 | 0 | Incomplete
| Update UML | Devon | 2018-11-04 | 2018-11-07 | 1 | 1.5 | Complete
| Course Time | All | 2018-10-31 | 2018-11-14 | 6 | 6 | Complete
Redefine Use Cases & Update Database/ Stored Procedures
|  | Stefana | 2018-10-31 | 2018-11-07 | 4 | 6 | Complete
|  | Devon | 2018-10-31 | 2018-11-07 | 4 | 6 | Complete
|  | Tyler | 2018-10-31 | 2018-11-07 | 4 | 0 | Incomplete
Initial System Build (MVC)
|  | Stefana | 2018-10-31 | 2018-11-07 | 15 | 15 | Complete
|  | Devon | 2018-10-31 | 2018-11-07 | 15 | 0 | Incomplete
|  | Tyler | 2018-10-31 | 2018-11-07 | 15 | 0 | Incomplete
Develop Testing Plan
|  | Stefana | 2018-11-12 | 2018-11-14 | 1 | 0 | Postponed
|  | Devon | 2018-11-12 | 2018-11-14 | 1 | 0 | Postponed
|  | Tyler | 2018-11-12 | 2018-11-14 | 1 | 0 | Postponed
Collect Stakeholder Feedback
|  | Stefana | 2018-11-14 | TBD | 1 | 1 | Feedback was gathered in class 11/14
|  | Devon | 2018-11-14 | TBD | 1 | 1 | Feedback was gathered in class 11/14
|  | Tyler | 2018-11-14 | TBD | 1 | 0 | Incomplete
Evaluate and Iterate
|  | Stefana | 2018-11-14 | TBD | 1.5 | 1.5 | Feedback was applied
|  | Devon | 2018-11-14 | TBD | 1 | 1 | Feedback was applied
|  | Tyler | 2018-11-14 | TBD | 1 | 0 | Incomplete
| Sprint 5 Milestone |  |  |  | 0 | 0
Overall |  |  |  |  | 82.5 | 46
Sprint 6: Deployment Planning | Finalize System Development
11/14/18 - 11/28/18 |  | Stefana | 2018-11-14 | 2018-11-28 | 20 | 20 | Complete
|  | Devon | 2018-11-14 | 2018-11-28 | 20 | 17 | Partial
|  | Tyler | 2018-11-14 | 2018-11-28 | 20 | 0 | Incomplete
Pre-Release Considerations
| Assumptions | Stefana | 2018-11-14 | 2018-11-28 | 2 | 3 | Complete
| Constraints | Devon | 2018-11-14 | 2018-11-28 | 2 | 1 | Partial
| Data Creation and Conversion | Tyler | 2018-11-14 | 2018-11-28 | 2 | 0 | Incomplete
| Course Time | All | 2018-11-14 | 2018-11-28 | 3 | 3 | Complete
Project Report Draft
|  | Stefana | 2018-11-14 | 2018-11-21 | 1 | 1 | Complete
|  | Devon | 2018-11-14 | 2018-11-21 | 1 | 1 | Complete
|  | Tyler | 2018-11-14 | 2018-11-21 | 1 | 1 | Complete
Design Documentation
|  | Stefana | 2018-11-14 | 2018-11-28 | 3 | 3 | Complete
|  | Devon | 2018-11-14 | 2018-11-28 | 3 | 2 | Partial
|  | Tyler | 2018-11-14 | 2018-11-28 | 3 | 2 | Partial
Testing Plan
|  | Stefana | 2018-11-14 | 2018-11-28 | 1 | 3 | Complete
|  | Devon | 2018-11-14 | 2018-11-28 | 1 | 1 | Complete
|  | Tyler | 2018-11-14 | 2018-11-28 | 1 | 0 | Incomplete
Deployment Plan
|  | Stefana | 2018-11-14 | 2018-11-28 | 1 | 3 | Complete
|  | Devon | 2018-11-14 | 2018-11-28 | 1 | 1 | Complete
|  | Tyler | 2018-11-14 | 2018-11-28 | 1 | 0 | Incomplete
Project Report
|  | Stefana | 2018-11-14 | 2018-11-28 | 1 | 2 | Complete
|  | Devon | 2018-11-14 | 2018-11-28 | 1 | 1 | Complete
|  | Tyler | 2018-11-14 | 2018-11-28 | 1 | 0 | Incomplete
| Sprint 6 Milestone |  |  |  | 0 | 0
Overall |  |  |  |  | 90 | 65
Sprint 7: Beta Testing & Final Product | Finalize Development
11/28/18 - 12/12/18 |  | Stefana | 2018-11-28 | 2018-12-12 | 10 | 10 | Complete
|  | Devon | 2018-11-28 | 2018-12-12 | 10 | 10 | Complete
|  | Tyler | 2018-11-28 | 2018-12-12 | 10 | 10 | Complete
Update Documentation
|  | Stefana | 2018-11-28 | 2018-12-12 | 5 | 5 | Complete
|  | Devon | 2018-11-28 | 2018-12-12 | 2 | 2 | Complete
|  | Tyler | 2018-11-28 | 2018-12-12 | 2 | 2 | Complete
| Course Time | All | 2018-11-28 | 2018-12-12 | 6 | 6 | Complete
Testing Strategy & Log
| Test Cases & Log | Stefana | 2018-11-28 | 2018-12-12 | 3 | 3 | Complete
| Test Cases & Log | Devon | 2018-11-28 | 2018-12-12 | 3 | 2 | Incomplete
| Test Cases & Log | Tyler | 2018-11-28 | 2018-12-12 | 3 | 0 | Incomplete
Collect Feedback
|  | Stefana | 2018-11-28 | 2018-12-12 | 1 | 1 | Complete
|  | Devon | 2018-11-28 | 2018-12-12 | 1 | 1 | Complete
|  | Tyler | 2018-11-28 | 2018-12-12 | 1 | 0 | Incomplete
Evaluate and Iterate
|  | Stefana | 2018-11-28 | 2018-12-12 | 1 | 1 | Complete
|  | Devon | 2018-11-28 | 2018-12-12 | 1 | 1 | Complete
|  | Tyler | 2018-11-28 | 2018-12-12 | 1 | 0 | Incomplete
Finalize Project Report Paper and Presentation
|  | Stefana | 2018-11-28 | 2018-12-12 | 3 | 4 | Complete
|  | Devon | 2018-11-28 | 2018-12-12 | 3 | 3 | Complete
|  | Tyler | 2018-11-28 | 2018-12-12 | 3 | 3 | Complete
Deliver project report, presentation and project
|  | Stefana | 2018-12-12 | 2018-12-12 | 1 | 1 | Complete
|  | Devon | 2018-12-12 | 2018-12-12 | 1 | 1 | Complete
|  | Tyler | 2018-12-12 | 2018-12-12 | 1 | 1 | Complete
| Sprint 7 Milestone |  |  |  | 0 | 0
Overall |  |  |  |  | 72 | 67
Total hours for the project |  |  |  |  | 589 | 410.5
72 total tasks
56 completed

## PM Schedule
Project Manager | Schedule
Stefana | 9/12 - 9/26 | TRUE
Tyler | 9/26 - 10/10 | TRUE
Devon | 10/10 - 10/24 | TRUE
Stefana | 10/24 - 11/7 | TRUE
Tyler | 11/7 - 11/21 | TRUE
Devon | 11/21 - 12/5 | TRUE
Stefana | 12/5 - 12/12 | TRUE